## Execution Plan
Phase | Task ID | Task Name | Description | Priority | Estimated Effort | Deliverables
Phase 1: EDA & Setup | 1.1 | Environment Verification | Verify GPU availability and install dependencies (pydicom, monai, timm, albumentations, pandas, openpyxl). | High | 2 Hours | Functional virtual environment with all required scientific libraries.
Phase 1: EDA & Setup | 1.2 | CSV Data Profiling | Analyze train.csv and train_series.csv to map unique study-to-series UIDs, check missing labels, and profile report languages. | High | 3 Hours | Detailed EDA notebook with language distribution and label frequency stats.
Phase 1: EDA & Setup | 1.3 | DICOM Image Inspection | Load sample DICOM images, check metadata (pixel spacing, orientation, manufacturer), and analyze slice dimensions/counts. | Medium | 4 Hours | Visualizations of slices along Sagittal, Coronal, and Axial planes.
Phase 2: Report Parsing | 2.1 | Multilingual Lexicon Creation | Gather clinical terms for the 12 target abnormalities across English, Spanish, Dutch, German, Turkish, Greek, and French. | High | 4 Hours | A dictionary mapping target classes to multilingual keywords.
Phase 2: Report Parsing | 2.2 | Negation Check Parser | Build regex/NLP patterns to handle negation structures (e.g., 'no tear', 'efüzyon izlenmedi') across different languages. | High | 6 Hours | Python NLP utility class that parses text and outputs class detection flags.
Phase 2: Report Parsing | 2.3 | Pseudo-Label Generation | Apply parser to 4,349 unlabeled reports. Validate parser accuracy on the 58 ground-truth studies to compute precision/recall. | High | 6 Hours | A generated CSV containing pseudo-labels / soft targets for all training studies.
Phase 3: Image Processing | 3.1 | DICOM Reader & Windowing | Implement DICOM pixel loading, rescale intercept/slope, and apply windowing/clipping to standardize contrast. | High | 6 Hours | Preprocessed raw array loader supporting min-max scaling.
Phase 3: Image Processing | 3.2 | 3D Resizing & Interpolation | Standardize slice thickness and resize/interpolate MRI series to a uniform size (e.g., 32 x 256 x 256). | High | 6 Hours | Function to resample volumes to consistent dimensions.
Phase 3: Image Processing | 3.3 | Plane Grouping & Pipeline | Group input scans by Anatomical Plane (Axial, Coronal, Sagittal) and write a PyTorch Dataset class. | High | 8 Hours | PyTorch Dataset loader returning processed multi-view tensors.
Phase 4: Model Architecture | 4.1 | 2.5D Slice Encoder | Create a feature extraction encoder using a pretrained 2D CNN (e.g., EfficientNet-B4 or ConvNeXt) from the timm library. | High | 6 Hours | Feature extractor neural net modules.
Phase 4: Model Architecture | 4.2 | Sequence Aggregator | Implement aggregation blocks (Global Pooling, GRU, or a Transformer Encoder) to merge slice-level features. | High | 8 Hours | Aggregated 3D spatial classification model.
Phase 4: Model Architecture | 4.3 | View Fusion Design | Combine predictions from Axial, Coronal, and Sagittal branches into a unified 12-class prediction head. | Medium | 6 Hours | Multi-view classification network model.
Phase 5: CV & Loss Strategy | 5.1 | Validation Split Setup | Set aside a hold-out test split of 20-30 ground-truth studies. Use GroupKFold (grouped by patient/study) on remaining data. | High | 4 Hours | Cross-validation index list mapped in train.csv.
Phase 5: CV & Loss Strategy | 5.2 | Soft-Label Loss Function | Implement a BCE loss function optimized for soft/pseudo labels, with positive class weight scaling. | High | 4 Hours | Custom PyTorch Loss module handles soft probability targets.
Phase 6: Model Training | 6.1 | 3D Augmentation | Implement 3D random rotations, flips, elastic transforms, and intensity shifts using albumentations/MONAI. | High | 6 Hours | Robust train data augmentation pipeline.
Phase 6: Model Training | 6.2 | Baseline View Training | Train individual models on Sagittal and Coronal views. Track validation macro-AUC on the 58 ground-truth labels. | High | 12 Hours | Weights of baseline Sagittal/Coronal model checkpoints.
Phase 6: Model Training | 6.3 | Hyperparameter Tuning | Tune learning rate, weight decay, and dropout. Evaluate performance improvement using validation ROC curves. | Medium | 10 Hours | Optimized model checkpoints with improved macro-AUC scores.
Phase 7: Inference & Submit | 7.1 | View Ensembling | Aggregate prediction logits from Axial, Coronal, and Sagittal models using a weighted average or meta-classifier. | High | 6 Hours | Ensembled predictions maximizing validation AUC.
Phase 7: Inference & Submit | 7.2 | Submission Notebook | Develop an offline-compliant Kaggle submission script. Include package wheel uploads and quick run checks. | High | 6 Hours | Functional Kaggle-ready submission file conforming to sample_submission.csv format.